## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Elisabeth Bernatska | 719-200-5445 | 24/7 | Mon - Fri
Abbey Beissler | 651-283-1705 | 24/7 | Mon - Fri
Holly Brouwer | 970-405-2361 | 24/7 | Mon - Fri
Brendan Desotell | 720-785-3014 | 24/7 | Mon - Fri

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Sue Jones
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWCoffeeMerchant | Data Warehouse | Coffee Merchant OLTP | Database | Database
DWCoffeeMerchant.dbo.FactSales | Fact Table | CoffeeMerchant.dbo.Sales | Table | Table
DWCoffeeMerchant.dbo.FullPrice | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Order_Line | smallint | int
DWCoffeeMerchant.dbo.Revenue | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Order_Line.dbo.Inventory | smallint | int
DWCoffeeMerchant.dbo.Profit | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Order_Line.dbo.Inventory.dbo.Employee.dbo.State | smallint | int
DWCoffeeMerchant.dbo.PriceofProduct | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Inventory | smallint | int
DWCoffeeMerchant.dbo.DiscountPrice | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Order_Line | smallint | int
DWCoffeeMerchant.dbo.TotalCommissionbyDate | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Employee | smallint | int
DWCoffeeMerchant.dbo.PricebyQuantity | Dimension Key Column | CoffeeMerchant.dbo.Sales.dbo.Order_Line | smallint | int
DWCoffeeMerchant.dbo.DimConsumer | Dimesion Table | CoffeeMerchant.dbo.Consumer | Table | Table
DWCoffeeMerchant.dbo.DimConsumer.ConsumerKey | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimStores.City | Dimension Column | CoffeeMerchant.dbo.Consumer.City | varchar(30) | nvarchar(40)
DWCoffeeMerchant.dbo.DimStores.State | Dimension Column | CoffeeMerchant.dbo.Consumer.State | char(2) | nchar(4)
DWCoffeeMerchant.dbo.DimStores.ZipCode | Dimension Column | CoffeeMerchant.dbo.Consumer.Zipcode | char(5) | nvarchar(8)
DWCoffeeMerchant.dbo.DimStores.CreditLimit | Dimension Column | CoffeeMerchant.dbo.Consumer.CreditLimit
DWCoffeeMerchant.dbo.DimEmployee | Dimesion Table | CoffeeMerchant.dbo.Employee | Table | Table
DWCoffeeMerchant.dbo.DimEmployee.EmployeerKey | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimEmployee.Name | Dimension Column | CoffeeMerchant.dbo.Employee.Name | nvarchar(25) | nvarchar(30)
DWCoffeeMerchant.dbo.DimEmployee.HireDate | Dimension Column | CoffeeMerchant.dbo.Employee.HireDate | date | datetime
DWCoffeeMerchant.dbo.DimEmployee.Gender | Dimension Column | CoffeeMerchant.dbo.Employee.Gender | char(1) | char(1)
DWCoffeeMerchant.dbo.DimEmployee.Age | Dimension Column | CoffeeMerchant.dbo.Employee.BirthDate | date | int
DWCoffeeMerchant.dbo.DimEmployee.CommissionRate | Dimension Column | CoffeeMerchant.dbo.Employee.CommissionRate | smallint | int
DWCoffeeMerchant.dbo.DimInventory | Dimesion Table | CoffeeMerchant.dbo.Inventory | Table | Table
DWCoffeeMerchant.dbo.DimInventory.InventoryKey | Dimension Key Column | Generated | na | int
DWCoffeeMerchant.dbo.DimInventory.Name | Dimension Column | CoffeeMerchant.dbo.Inventory.Name | nvarchar(50) | nvarchar(75)
DWCoffeeMerchant.dbo.DimInventory.Price | Dimension Column | CoffeeMerchant.dbo.Inventory.Price | smallint | int
DWCoffeeMerchant.dbo.DimInventory.ItemType | Dimension Column | CoffeeMerchant.dbo.Inventory.ItemType | char(1) | char(1)
DWCoffeeMerchant.dbo.DimInventory.Country | Dimension Column | CoffeeMerchant.dbo.Inventory.Country | char(20) | char(30)
DWCoffeeMerchant.dbo.DimDate | Dimesion Table | na | na | Table
DWCoffeeMerchant.dbo.DimDate.DateKey | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDate.HolidayFlag | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.HolidayFlagName | Dimension Column | na | na | varchar(10)
DWCoffeeMerchant.dbo.DimDate.Season | Dimension Column | na | na | varchar(10)
DWCoffeeMerchant.dbo.DimDate.SeasonName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.DayofMonthName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.DayofMonth | Dimension Column | na | na | varchar(10)
DWCoffeeMerchant.dbo.DimDate.DayofWeekName | Dimension Column | na | na | datetime
DWCoffeeMerchant.dbo.DimDate.DayofWeek | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.Month | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDate.MonthName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.Quarter | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDate.QuarterName | Dimension Column | na | na | nvarchar(50)
DWCoffeeMerchant.dbo.DimDate.Year | Dimension Column | na | na | int
DWCoffeeMerchant.dbo.DimDate.YearName | Dimension Column | na | na | nvarchar(50)
Object Name | Description | Source | Source Type | Destination Type

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description